## Slide 1: CPM

## Slide 10: Convention we will be using
ES | Activity | EF
LS | duration | LF
Forward pass
EF = ES + activity duration
Backward pass
LS = LF - activity duration

## Slide 12
Forward Pass
Forward pass
EF = ES + activity duration
0 | B | 0+10=10
 | 10 | 

## Slide 13
Forward Pass
Forward pass
EF = ES + activity duration
0 | B | 0+10=10
 | 10 | 
0 | C | 0+20=20
 | 20 | 

## Slide 14
Forward Pass
Forward pass
EF = ES + activity duration
0 | B | 0+10=10
 | 10 | 
20 | E | 20+20=40
 | 20 | 

## Slide 15
Forward Pass
Forward pass
EF = ES + activity duration
20 | D | 20+30=50
 | 30 | 
20 | E | 20+20=40
 | 20 | 

## Slide 16
Forward Pass
Forward pass
EF = ES + activity duration
20 | D | 20+30=50
 | 30 | 
40 | F | 40+40=80
 | 40 | 

## Slide 17
Forward Pass
Forward pass
EF = ES + activity duration
80 | G | 80+20=100
 | 20 | 
40 | F | 40+40=80
 | 40 | 

## Slide 18
Forward Pass
Forward pass
EF = ES + activity duration

## Slide 19
Backward Pass
LS = LF - activity duration
ES | Activity | EF
LS | duration | LF
80 | G | 100
100-20=80 | 20 | 100

## Slide 20
Backward Pass
LS = LF - activity duration
40 | F | 80
80-40=40 | 40 | 80

## Slide 21
Backward Pass
LS = LF - activity duration
20 | D | 50
80-30=50 | 30 | 80

## Slide 22
Backward Pass
LS = LF - activity duration
20 | E | 40
40-20=20 | 20 | 40

## Slide 23
Backward Pass
LS = LF - activity duration
0 | C | 20
20-20=0 | 20 | 20

## Slide 24
Backward Pass
LS = LF - activity duration
0 | B | 10
20-10=10 | 10 | 20

## Slide 25
Slack Time
Slack event time is the free time that an event has to stay on it's necessary time track.
All events that are involved in the critical path will have a slack time of 0 because there is no extra time available for that event.
Slack = LF-EF
Critical Path : A-C-E-F-G-H