## Slide 1: WEEK 6 Critical Path Method(CPM)
Project Management Continued..

## Slide 2: Question 1
Activity | Predecessor | Duration
A | (None) | 5 months
B | (None) | 3
C | (None) | 4
D | A | 2
E | C | 4
F | A | 5
G | B,D,E | 6

## Slide 3: Question 2
Activity | Predecessor | Duration
A | (None) | 5 months
B | A | 4
C | A | 5
D | B | 6
E | C | 3
F | D,E | 4

## Slide 4: Question 3
Activity | Predecessor | Duration
A | (None) | 5 months
B | (None) | 2
C | A | 4
D | B | 6
E | A | 3
F | C,D | 3
G | E | 5